## Summary
Personal Accident (PA001) – UAT Summary
Date | 2026-10-14
Scope | Plans, premium, covers and generated outputs (API has no input validation by design)
PASS | 45
FAIL | 10
OBSERVATION | 5
Total | 60

## Test Cases & Results
Test ID | Module | Test Case | Priority | Expected | Actual | Status
PA-PLAN-01 | Get Plans | Get Plans (With TTD) returns Plans 1-5 | High | 5 plans | plans ['1', '2', '3', '4', '5'] | PASS
PA-PLAN-02 | Get Plans | Get Plans (Without TTD) returns Plans 1-5 | High | 5 plans | plans ['1', '2', '3', '4', '5'] | PASS
PA-PLAN-11 | Get Plans | Covers & sums insured – With TTD Plan 1 per spec | High | per spec 'Coverages and Sum Assured' | {'PPD': 12000, 'REX': 1500, 'ACD': 12000, 'PTD': 12000, 'TTD': 3000, 'HCB': 20} | PASS
PA-PLAN-12 | Get Plans | Covers & sums insured – With TTD Plan 2 per spec | High | per spec 'Coverages and Sum Assured' | {'TTD': 3000, 'HCB': 20, 'PTD': 22000, 'REX': 1500, 'PPD': 22000, 'ACD': 22000} | PASS
PA-PLAN-13 | Get Plans | Covers & sums insured – With TTD Plan 3 per spec | High | per spec 'Coverages and Sum Assured' | {'ACD': 32000, 'PPD': 32000, 'HCB': 20, 'TTD': 3000, 'PTD': 32000, 'REX': 1500} | PASS
PA-PLAN-14 | Get Plans | Covers & sums insured – With TTD Plan 4 per spec | High | per spec 'Coverages and Sum Assured' | {'TTD': 3000, 'PTD': 42000, 'REX': 1500, 'PPD': 42000, 'HCB': 20, 'ACD': 42000} | PASS
PA-PLAN-15 | Get Plans | Covers & sums insured – With TTD Plan 5 per spec | High | per spec 'Coverages and Sum Assured' | {'HCB': 20, 'ACD': 52000, 'PPD': 52000, 'REX': 1500, 'TTD': 3000, 'PTD': 52000} | PASS
PA-PLAN-21 | Get Plans | Covers & sums insured – Without TTD Plan 1 per spec | High | per spec 'Coverages and Sum Assured' | {'PPD': 10000, 'ACD': 10000, 'HCB': 20, 'REX': 1500, 'PTD': 10000} | PASS
PA-PLAN-22 | Get Plans | Covers & sums insured – Without TTD Plan 2 per spec | High | per spec 'Coverages and Sum Assured' | {'PTD': 20000, 'REX': 1500, 'PPD': 20000, 'ACD': 20000, 'HCB': 20} | PASS
PA-PLAN-23 | Get Plans | Covers & sums insured – Without TTD Plan 3 per spec | High | per spec 'Coverages and Sum Assured' | {'REX': 1500, 'PTD': 30000, 'HCB': 20, 'ACD': 30000, 'PPD': 30000} | PASS
PA-PLAN-24 | Get Plans | Covers & sums insured – Without TTD Plan 4 per spec | High | per spec 'Coverages and Sum Assured' | {'PPD': 40000, 'REX': 1500, 'ACD': 40000, 'HCB': 20, 'PTD': 40000} | PASS
PA-PLAN-25 | Get Plans | Covers & sums insured – Without TTD Plan 5 per spec | High | per spec 'Coverages and Sum Assured' | {'HCB': 20, 'PPD': 50000, 'REX': 1500, 'PTD': 50000, 'ACD': 50000} | PASS
PA-PREM-90 | Premium & Covers | Total Sum Insured equals the selected plan's benefits (single plan in PlanList) | High | With TTD Plan 1 = 40,520 | All 20 proposals: SumInsured is 2× the plan (With TTD Plan 1: 81,040 vs 40,520; Without TTD Plan 1: 63,040 vs 31,520); PlanList has 2 entries, the 2nd without PlanId/PlanName. Same defect as Term Life DEF-01. | FAIL
PA-PREM-A11 | Premium & Covers | Annual – With TTD Plan 1: premium, commission, covers | Critical | premium 68 commission 44.1 | PPA0010000000290 prem=68 comm=44.1 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A12 | Premium & Covers | Annual – With TTD Plan 2: premium, commission, covers | Critical | premium 96 commission 63.7 | PPA0010000000291 prem=96 comm=63.7 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A13 | Premium & Covers | Annual – With TTD Plan 3: premium, commission, covers | Critical | premium 124 commission 83.3 | PPA0010000000292 prem=124 comm=83.3 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A14 | Premium & Covers | Annual – With TTD Plan 4: premium, commission, covers | Critical | premium 152 commission 102.9 | PPA0010000000293 prem=152 comm=102.9 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A15 | Premium & Covers | Annual – With TTD Plan 5: premium, commission, covers | Critical | premium 180 commission 122.5 | PPA0010000000294 prem=180 comm=122.5 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A21 | Premium & Covers | Annual – Without TTD Plan 1: premium, commission, covers | Critical | premium 55 commission 35 | PPA0010000000295 prem=55 comm=35 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A22 | Premium & Covers | Annual – Without TTD Plan 2: premium, commission, covers | Critical | premium 81 commission 53.2 | PPA0010000000296 prem=81 comm=53.2 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A23 | Premium & Covers | Annual – Without TTD Plan 3: premium, commission, covers | Critical | premium 109 commission 72.8 | PPA0010000000297 prem=109 comm=72.8 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A24 | Premium & Covers | Annual – Without TTD Plan 4: premium, commission, covers | Critical | premium 137 commission 92.4 | PPA0010000000298 prem=137 comm=92.4 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-A25 | Premium & Covers | Annual – Without TTD Plan 5: premium, commission, covers | Critical | premium 165 commission 112 | PPA0010000000299 prem=165 comm=112 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S11 | Premium & Covers | Single – With TTD Plan 1: premium, commission, covers | Critical | premium 68 commission 44.1 | PPA0010000000300 prem=68 comm=44.1 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S12 | Premium & Covers | Single – With TTD Plan 2: premium, commission, covers | Critical | premium 96 commission 63.7 | PPA0010000000301 prem=96 comm=63.7 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S13 | Premium & Covers | Single – With TTD Plan 3: premium, commission, covers | Critical | premium 124 commission 83.3 | PPA0010000000302 prem=124 comm=83.3 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S14 | Premium & Covers | Single – With TTD Plan 4: premium, commission, covers | Critical | premium 152 commission 102.9 | PPA0010000000303 prem=152 comm=102.9 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S15 | Premium & Covers | Single – With TTD Plan 5: premium, commission, covers | Critical | premium 180 commission 122.5 | PPA0010000000304 prem=180 comm=122.5 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S21 | Premium & Covers | Single – Without TTD Plan 1: premium, commission, covers | Critical | premium 55 commission 35 | PPA0010000000305 prem=55 comm=35 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S22 | Premium & Covers | Single – Without TTD Plan 2: premium, commission, covers | Critical | premium 81 commission 53.2 | PPA0010000000306 prem=81 comm=53.2 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S23 | Premium & Covers | Single – Without TTD Plan 3: premium, commission, covers | Critical | premium 109 commission 72.8 | PPA0010000000307 prem=109 comm=72.8 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S24 | Premium & Covers | Single – Without TTD Plan 4: premium, commission, covers | Critical | premium 137 commission 92.4 | PPA0010000000308 prem=137 comm=92.4 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-PREM-S25 | Premium & Covers | Single – Without TTD Plan 5: premium, commission, covers | Critical | premium 165 commission 112 | PPA0010000000309 prem=165 comm=112 ¦ premium, commission and all covers match spec (total SumInsured doubled – see PA-PREM-90) | PASS
PA-LC-01 | Lifecycle | Update proposal: plan change re-prices (68→124) and updates covers | Critical | premium 124, ACD 32000 | Plan 1→3: premium 124, ACD 32000 | PASS
PA-LC-02 | Lifecycle | Update proposal: switch With→Without TTD removes TTD cover | High | premium 81, no TTD | With→Without TTD, Single, term 3: premium 81; covers {'ACD': 20000, 'PTD': 20000, 'PPD': 20000, 'HCB': 20, 'REX': 1500} | PASS
PA-LC-03 | Lifecycle | Load proposal returns latest saved data | High | premium 81 | load → PPA0010000000312 prem 81 | PASS
PA-LC-04 | Lifecycle | Issue policy (POPA001########, Effective) | Critical | PolicyStatus 2 | POPA00100000141 ProposalStatus 3 PolicyStatus 2 | PASS
PA-LC-05 | Lifecycle | Load policy by PolicyNo | High | same data | POPA00100000141 prem 81 | PASS
PA-LC-06 | Lifecycle | Proposal reject sets status Rejected (4) | Critical | status 4 | reject 200 {'message': 'checker rejected', 'status': 'SUCCESS'}; status after 4 | PASS
PA-LC-07 | Lifecycle | Re-issue of issued proposal | Medium | no duplicate policy | Re-issue of issued proposal → HTTP 500 : java.lang.RuntimeException: Error occured while calling iHub integration service at url https://uponlyuat-sandbox-in.insuremo.com/api/uponlyuat/api-orchestration/v1/flow/issue-policy, StatusError : | OBSERVATION
PA-DOC-01 | Documents | Application form (With TTD, Plan 3): sum insured against each benefit | Critical | Death 32000, PTD 32000, PPD 32000, TTD 3000 (50/week), HCB 20, REX 1500 | With-TTD Plan 3 application form prints cover amounts against the wrong benefits: Death due to an accident = 20 (spec 32000), PPD = 3000 (spec 32000), TTD = 32000 (spec 3000), Hospital Cash = 32000 (spec 20). Only PTD 32000 and Repatriation 1500 are right. Evidence: application PDF page 1. | FAIL
PA-DOC-02 | Documents | Certificate (With TTD, Plan 3): sum insured against each benefit | Critical | Death 32000, PTD 32000, PPD 32000, TTD 3000, HCB 20, REX 1500 | With-TTD Plan 3 certificate shows the same wrong mapping: Death 20, PTD 32000, PPD 3000, TTD 32000, Hospital Cash 32000, REX 1500. Re-test with 4 different cover orders in the request gave 4 different (all wrong) layouts – mapping is by position, not by cover code. | FAIL
PA-DOC-03 | Documents | Certificate/application (Without TTD, Plan 2): benefit rows & amounts | High | Death 20000, PTD 20000, PPD 20000, HCB 20, REX 1500 and no TTD row | Without-TTD Plan 2 certificate: prints a 'TTD due to an accident' row (20000) and 'Hospital Cash' row (20000) – neither is a Without-TTD benefit with that amount; Death = 20, PPD blank. Application form (Without TTD): Death 20, PTD 20000, PPD blank, no Hospital Cash row. | FAIL
PA-DOC-04 | Documents | Application form (Without TTD): all five benefits listed with amounts | High | no TTD | Application form (Without TTD) omits the Hospital Cash Benefit row and leaves PPD blank (see PA-DOC-03). | FAIL
PA-DOC-05 | Documents | Application form cancellation clause prints 80% | High | 80% | PA application form also prints '8096 of the unearned Premium' | FAIL
PA-DOC-06 | Documents | Premium wording for Single premium policies | Medium | 'Single Premium' / one-time amount | Single-premium policy (Plan 2 Without TTD, 4 yrs): application form text says 'pay the Annual Premium … 81 Yearly'; certificate shows 'OMR 81 Yearly' beside 'Payment Frequency: Single Premium'. | FAIL
PA-DOC-07 | Documents | Certificate 'Period of Cover' English and Arabic agree | Medium | same number of years | English '1 Year(s)' / '4 Year(s)' but Arabic line shows '5 سنوات' in both certificates (looks hard-coded). | FAIL
PA-DOC-08 | Documents | Application form layout artefacts | Low | clean form | Stray text 'ssss' printed before 'Premium (OMR)'; footer 'Page 1 of' clipped; 'Application No' prints the ProposalNo (PPA…), not the entered ApplicationNo. | FAIL
PA-FEED-01 | Feed File | Feed generated for PA001 | High | rows | 30 columns, 3 rows | PASS
PA-FEED-02 | Feed File | Product Name correct for PA | High | Personal Accident with/without TTD | Product names ['Personal Accident with TTD', 'Personal Accident without TTD'] | PASS
PA-FEED-03 | Feed File | Feed row values (premium, frequency, term, product) per policy | High | match | premium/frequency/term/product OK for both | PASS
PA-FEED-04 | Feed File | Cancelled Date blank for Effective policies | High | blank | 3/3 Effective policies carry a Cancelled Date | FAIL
PA-FEED-05 | Feed File | Feed has Branch Code, LCCode, LGCode | Low | present | Feed has Branch Code, LC Code and LG Code (30 columns). Unlike the Term Life feed, nothing is missing. | PASS
PA-CAN-01 | Cancellation | Cancel-check for PA001 | Medium | Per business | cancel-check → HTTP 400 'Cancellation through this API is not enabled for product PA001'. PA cancellation (free-look, pro-rata, approve) could not be tested; confirm whether PA cancellation is in scope/enabled. | OBSERVATION
PA-COL-01 | Collection check | Proposal request without ChannelCode (as in collection) works | Medium | 200 | PPA0010000000310 prem 68 | PASS
PA-COL-02 | Collection check | Sample 'Proposal API' body (sub 2 + TTD cover) executes | Medium | 200 | Collection 'Proposal API' as-is (ProductSubcode 2 = Without TTD but TTD cover sent): HTTP 500 : java.lang.RuntimeException: Error occured while calling iHub integration service at url https://uponlyuat-sandbox-in.insuremo.com/api/uponlyuat/api-orchestration/v1/flow/create-update-quote, StatusE – the sample is for Without TTD but still sends a TTD cover; remove TTD from the body. | OBSERVATION
PA-COL-03 | Collection check | Without-TTD proposal with correct cover list works | Medium | 200 | Without TTD with correct 5 covers → PPA0010000000311 | PASS
PA-COL-04 | Collection check | 'doc_generation PDF' sample body (no ProductCode) runs | Medium | PDF | Collection sample 'doc_generation PDF' (no ProductCode/ChannelCode) → {"validateResult":{"brokerName":"UPONLY","errors":[{"code":"","message":"ProductCode is missing in request. Expected 'PA001' or 'TL001'"}],"functionName":"loadP | OBSERVATION
PA-COL-05 | Collection check | 'doc_generation PDF Copy' → application_doc_generation endpoint | Low | PDF | HTTP 200, PDF (legacy endpoint) | PASS
PA-COL-06 | Collection check | print/template (foundation gateway) | Low | PDF | print/template (foundation gateway, separate host/token) with our UAT token → HTTP 403 {"env":"aws_in_insuremo_uat","trace":"83dbb42996c94caf13f1429c92347425","env_name":"aws_in_insuremo_uat","trace_id":"83d | OBSERVATION

## Defects
ID | Severity | Module | Title | Description | Tests | Recommendation
PA-DEF-01 | Critical | Documents | Application form and certificate (With TTD) print sums insured against the wrong benefits | Plan 3: Death shows 20 (spec 32000), PPD 3000 (spec 32000), TTD 32000 (spec 3000), Hospital Cash 32000 (spec 20). Amounts are mapped by position of the cover in the request, not by cover code: sending the same covers in 4 different orders gave 4 different wrong layouts. The customer certificate states wrong covers. | PA-DOC-01, PA-DOC-02 | Map document values by ProductElementCode (ACD/PTD/PPD/TTD/HCB/REX), not by sequence.
PA-DEF-02 | High | Documents | Without-TTD application form and certificate show wrong benefit rows | Certificate prints a TTD row and a Hospital Cash row at 20000, leaves PPD blank and Death = 20. Application form omits Hospital Cash and leaves PPD blank. Spec: Death/PTD/PPD 20000, HCB 20, REX 1500, no TTD. | PA-DOC-03, PA-DOC-04 | Use a Without-TTD layout and map by cover code.
PA-DEF-03 | High | Create Proposal | Total Sum Insured doubled (duplicate empty plan in PlanList) | All 20 PA proposals: With TTD Plan 1 SumInsured 81,040 vs 40,520; Without TTD Plan 1 63,040 vs 31,520. 2nd PlanList entry has no PlanId/PlanName. Same as Term Life DEF-01. | PA-PREM-90 | Return only the selected plan; fix roll-up.
PA-DEF-04 | Medium | Documents | Single-premium policies show 'Annual'/'Yearly' wording and wrong Arabic period | Application: 'pay the Annual Premium … 81 Yearly' for a Single-premium policy; certificate 'OMR 81 Yearly' next to 'Single Premium'. Arabic 'Period of Cover' always shows 5 years (English 1 / 4). | PA-DOC-06, PA-DOC-07 | Switch wording by PremiumMode; bind Arabic period to the term.
PA-DEF-05 | Medium | Feed File | Cancelled Date filled for Effective policies | 3 of 3 Effective PA policies carry a Cancelled Date equal to the issue timestamp. (Same as Term Life DEF-03.) | PA-FEED-04 | Populate only for cancelled policies.
PA-DEF-06 | Low | Documents | Application form artefacts | Stray 'ssss' before 'Premium (OMR)'; footer 'Page 1 of' clipped; cancellation clause prints '8096 of the unearned Premium' (should be 80%); 'Application No' shows ProposalNo. | PA-DOC-05, PA-DOC-08 | Fix template.

## Collection Review
Request | Finding
Update Proposal API | Sample targets PPA0010000000001, which is already issued → 'proposal status shows it has been issued already, can not be update/issue again' (500). Use an un-issued proposal.
Load Policy API | Works (POPA00100000091 Effective).
Get Plan API / Copy | Work; Sub 1 = With TTD, Sub 2 = Without TTD, plans/covers match spec.
Proposal API | Sample (ProductSubcode 2 = Without TTD) sends a TTD cover → 500 PlanAutoPopulate 'BenefitCode on null'. Remove TTD from the cover list.
Proposal API Copy | Works (With TTD Plan 1, premium 68).
issuePolicy API | Sample proposal already issued → 500 (same as update). Use a fresh proposal.
Data Table API | Works (Relationship Id 2 = Daughter).
Token | Works; collection tokens in the headers are expired – use a variable set by a Token test script.
generate-feedfile | Works (xlsx).
Proposal Reject | Works (PPA0010000000030 → SUCCESS).
print/template | Different host (sandbox-in-gw) and token – returns 403 with the UAT token; could not be tested.
doc_generation PDF | Body lacks ProductCode (and ChannelCode) → 'ProductCode is missing in request. Expected PA001 or TL001'; the body also has // comments (invalid JSON for some tools).
doc_generation PDF Copy | Uses legacy application_doc_generation endpoint; works (PDF).
General | Hard-coded bearer tokens and a plaintext password in the collection – rotate and use variables. ChannelCode is missing in most samples (still works).