## README
Item | Value
Document | Afillar Insurance API - UAT deployment checklist v1.1 (companion to the UAT Deployment Plan)
Source | MC tenant `uponly`, profile portal:uponly
Target | UAT - tenant code / profile / gateway: <TO BE PROVIDED>
How to use | Work sheets in order: 1 Prerequisites, 2 Functions, 3 APIs, 4 Tables, 5 Platform config, 6 Environment values, 7 Steps, 8 Smoke tests, 9 Go/No-go. Set Status to Done/Failed and fill Evidence.
Rule | PA001 is never changed. Ids differ per tenant: re-resolve, never copy.

## 1 Prerequisites
# | Prerequisite | Owner | Status | Evidence
1 | UAT tenant code, imo profile and gateway received | Project | Open
2 | Deployer has admin rights: iComposer, iTables, product config, Output Service, code tables | Platform | Open
3 | PA001 exists in UAT (or tech/market products can be created) | Platform | Open
4 | API users with Checker and Approver roles created for Sohar Bank | Platform | Open
5 | Gateway routes /up/... allowed to the partner | Platform | Open
6 | Backup/export of UAT iComposer and iTables taken | Deployer | Open
7 | Release package v1.1 extracted; sources match MC md5 list (sheets 2-3) | Deployer | Open
8 | Change window approved | PM | Open

## 2 Functions
Order | Function | MC version | MC md5 | Lines | Status | Evidence
1 | UPDataUtil | 9 | 934ae12b563eb7c410d207a7f1821c87 | 234 | Open
2 | UPSecurity | 4 | a10494d853e972eb3a14cd2f7890f2e3 | 115 | Open
3 | UPErrorHandler | 9 | 3f42fef143df48bc6d8804ee65c10d32 | 99 | Open
4 | UPPlatformClient | 7 | 8e925c530f83fe1d3ab6738ecaa25bd2 | 48 | Open
5 | UPValidator | 3 | 11a5b703d52e0457e62278ade6abcf4c | 333 | Open
6 | UPProductData | 4 | 7c8b8d30cafa6784f20d2177e0d055af | 201 | Open
7 | UPShaper | 3 | cae845cc83483832aac1df48f199f9d6 | 125 | Open
8 | UPDocBuilder | 3 | 7cf4a157c4236f187844e5ff7cd70ba5 | 194 | Open
9 | UPDocService | 4 | 8606b0a5d1b673ab1be6ec8b53fd9f19 | 104 | Open
10 | UPCancelService | 7 | 232c9e0e0b807c0957f16c0eebb5efe9 | 302 | Open

## 3 APIs
Name | Route | Method | MC version | MC md5 | UAT version | Status | Evidence
UPApplicationDocGeneration | /up/application_doc_generation | POST | 7 | 0818aeec73ab2ebe2b3d2290f698b74e |  | Open
UPCancelApprove | /up/cancel-approve | POST | 5 | 7ba502722a340a3a0ca395ae322f7d8f |  | Open
UPCancelCheck | /up/cancel-check | POST | 5 | ab65f1fe0f4620552e505b9065a1dc95 |  | Open
UPCommissionQuery | /up/commission-query | POST | 10 | 144617f0618a9106d406da9ac549a1cb |  | Open
UPDocGeneration | /up/doc_generation | POST | 7 | 505d753dc554eb20de00919ff28758d4 |  | Open
UPFeedFile | /up/generate-feedfile | POST | 9 | 191ab6f5829dd3d304aa128d1ea5b2e1 |  | Open
UPGetPlans | /up/get-plans | POST | 7 | 279231cf013f6d532155d4085e006d14 |  | Open
UPIssue | /up/issue | POST | 9 | 467185f6ca0ff488a2d26a24ff0e75ec |  | Open
UPListMasterTable | /up/list-master-table | POST | 7 | c7e9a27e99efc9ce9997ccf2779bab0d |  | Open
UPLoadPolicy | /up/load-policy | GET | 7 | 2157203c2f115dca0a4cba80505ec9b9 |  | Open
UPProposal | /up/proposal | POST | 6 | 6a664918a95f068e4d8cd3f2782dae77 |  | Open
UPProposalReject | /up/proposal-reject | POST | 9 | 01c301ef0c8d1aece7e300e333edce8b |  | Open
UPUpdateProposal | /up/update-proposal | POST | 9 | 12f3b6a05faf4e07209b1b19b6809cd8 |  | Open

## 4 Tables
Table | Rows (MC) | Action | Status | UAT row count / evidence
UP_Channel | 1 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_Carrier | 1 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_ProductMaster | 11 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_ProductRule | 11 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_ProductPlanRelation | 57 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_PlanBenefitRelation | 148 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_DocTemplate | 22 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_DocWording | 27 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_BenefitText | 21 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_FeedColumn | 29 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_FieldRule | 138 | Create table, load rows with record-batch-save (insert-only); verify count | Open
UP_ApiConfig | 81 | Create table, load rows with record-batch-save (insert-only); verify count | Open

## 5 Platform config
Item | Detail | Status | Evidence
Tech products (7) + market products (7) | UPPA001, TL001, FP001, HC001, CI001, LP001, DH001: recreate/import, re-resolve product ids | Open
Data dictionary bindings | incl. cancellation fields and OrgCode/PubBranch value 1 | Open
Rating / plan / benefit data | per product | Open
Output templates (14) and DocTemplate rows | re-resolve template ids in UP_DocTemplate | Open
Code tables | PubBranch 1, gender, ID type, marital status, relationship | Open
Pre-existing tenant tables | BranchCode, Relationship etc. must exist in UAT | Open

## 6 Environment values
Setting | Meaning | UAT value | Status | Evidence
AllowedHosts | UAT gateway host |  | Open
GatewayUrl | UAT gateway URL |  | Open
PrintUrl | UAT print service URL |  | Open
UP_Channel row | partner ChannelCode for UAT |  | Open
Token endpoint / client | UAT OAuth client for the partner |  | Open
OrgCode | branch value 1 must exist as PubBranch |  | Open

## 7 Steps
# | Step | Owner | Status | Evidence
1 | Export MC sources and rows (already in the package) | Deployer | Open
2 | Create the 12 UP_ tables in UAT | Deployer | Open
3 | Load rows; adjust environment keys (sheet 6) | Deployer | Open
4 | Configure/verify products and templates, re-resolve ids | Deployer | Open
5 | Push the 10 functions in the order of sheet 2 | Deployer | Open
6 | Push the 12 APIs (sheet 3), compile check on each | Deployer | Open
7 | Reload / publish routes and gateway mapping | Deployer | Open
8 | Run smoke tests (sheet 8) | Deployer | Open
9 | Run PA001 snapshot before/after and compare | Deployer | Open
10 | Sign off with go / no-go (sheet 9) | Deployer | Open

## 8 Smoke tests
Product | Test | Status | Evidence
UPPA001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
TL001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
FP001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
HC001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
CI001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
LP001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
DH001 | carrier_check.py flow: Get Plans, Proposal, Issue, Load, Cancel Check/Approve, Commission; CarrierCode AFIC | Open
All | Mismatched CarrierCode returns 400 | Open
All | Master data lists UP_Carrier | Open
All | security_probe.py (read-only checks) | Open

## 9 Go-NoGo
Criterion | Decision | Comment
All functions and APIs match MC md5 / version
All 12 tables have the MC row counts
7 product smoke flows pass
PA001 snapshot identical before/after
Security probe has no new findings vs MC
Partner users and routes confirmed
Rollback tested (re-push saved sources)